## Dashboard
Project: Trio Going VirAl
Description: Creation of social media pages and YouTube Channel to create Viral Content.
Owner: Dibyendu Ghatak, Sumit Gupta, Atanu Das
Status: Draft
Key Docs | Description
Project charter | An overview of the project, key elements and expectations
Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially.
Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized.
Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle.
Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion.
Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know
Shared folder | Folder with all relevant documentation
RACI chart | Identifies who is responsible, accountable, consulted and informed within the project.
Note on A7: Add hyperlink to digital document, Project charter
Note on A8: Add hyperlink to digital document, Statement of work
Note on A9: Add hyperlink to digital document, risk management plan
Note on A13: Add hyperlink to a shared folder
Note on A14: Add hyperlink to RACI chart spreadsheet

## RACI Chart
Trio Going VirAl
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy |  | Dibyendu G. | Atanu D. | Sumit G. | NA | NA
PHASE 1
Task/Deliverable
1. Logo Designing |  | R | A | C
2. Facebook Page Creation |  | I | R | I
3. Instagram Page Creation |  | I | I | R
4. YouTube channel creation |  | I | R | I
5. Content Idea |  | A | A | R
6. First Content Script |  | C | C | A
7. Gameplay Video creation |  | A | R | I
8. Editing |  | R | A | C

## Project Schedule
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: Project Manager | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Get 500 subs/likes/followers | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | [5 empty] | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | [5 empty] | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | [5 empty] | 0% | bar: MARCH M 29 to APRIL F 9
2 | Get 2000 subs/likes/followers
2.1 | [5 empty] | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | [5 empty] | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | [5 empty] | 0% | bar: APRIL M 19 to APRIL F 30
3 | Get 5000 subs/likes/followers
3.1 | [5 empty] | 0% | bar: MAY M 3 to MAY F 14
3.2 | [5 empty] | 0% | bar: MAY M 17 to MAY F 28
3.3 | [5 empty] | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Budget: Trio Going VirAl
[7 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 0 | 0 | 0
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S)
Milestone 1: Get 500 subs/likes/followers
Task 1: | -- |  |  | 0 | 0 |  | 0 |  | 0
Task 2: | -- |  |  | 0 | 0 |  | 0 |  | 0
Task 3: |  | 0 | 0 |  |  |  | 0 |  | 0
[6 empty] | Total | 0 | 0
Milestone 2: Get 2000 subs/likes/followers
Task 1: | -- |  |  |  |  | 0 | 0 |  | 0
[6 empty] | Total | 0 | 0
Milestone 3: Get 5000 subs/likes/followers
Task 1: |  | 0 | 0 |  |  |  | 0 |  | 0
Task 2: |  | 0 | 0 |  |  |  | 0 |  | 0
Task 3: |  | 0 | 0 |  |  |  | 0 |  | 0
[6 empty] | Total | 0 | 0
Reserve buffer | [6 empty] | 5
TOTAL | [6 empty] | 5 | 0

## Communication Plan
Trio Going VirAl communication plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Atanu Das | Every Sunday at 2:30pm | Email (from individual address) | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | Check in with the team about high level of questions beforehand.
|  | One time | Dibyendu Ghatak |  | In Person
|  | Weekly | Sumit Gupta |  | In Person
|  | Weekly | Atanu Das |  | In Person
|  | Weekly | Atanu Das |  | In Person
|  | Weekly | Atanu Das |  | In Person
|  | Daily | Atanu Das |  | In Person
|  | One time | Atanu Das |  | In Person
|  | Weekly | Atanu Das |  | In Person
|  | One time | Atanu Das |  | In Person